## Slide 1: European Soccer Database: A Data Analysis Project (IFN701)
By: bhullar, harmandeep kaur
Student Id : n9784098

## Slide 2: Project overview:
Core idea and Project Scope:
A Kaggle challenge dataset to produce interesting insights by visualising and analysing the European soccer matches dataset.
This exciting dataset is about more than 25,000 matches, 10,000+ players from 11 European Countries with their lead championship from seasons 2008 to 2016.
I am particularly interested in players attributes and teams as I want to analyse and compare the characteristics/features of best players and their performance of top 10 players in their home country versus away country.
Deliverables:
CSV and SQLite file/dataset
R markdown file
Project report

## Slide 3: Problem Space and Motivation:
Kaggle challenge and very exciting dataset to explore and produce interesting insights about European soccer matches and players.
Its always very hard to predict the soccer match results and its not obvious like best team always win or team with top/best players is a best team.
So, what kind of factors affects the match results like best/top players in team/home or away country match/ characteristics of players etc.
In this project, I want to develop a model to predict the performance of players and results of matches by analyzing the characteristics of players and other factors which affects the results of match.

## Slide 4: Anticipated significance:
Nowadays many professional betting agencies are making a lot of money by predicting match results. So, it means betting odds are calculated to increase the profits and minimize their risks(wrong predictions).
I want to analyze the factors that affect the results of matches and performance of players for example location of match characteristics of players/team mates/best players etc.
Moreover its already known that the top 20/ best players from season 2008 to 2016. so, it can be significant to create a model to predict results by using existing knowledge.

## Slide 5: Project methodology
Stage 1: define a question of interest
Stage 2: define the ideal dataset
Stage 3: acquire the data
Stage 4: clean the data
Stage 5: explore the data
Stage 6: statistical prediction and modelling of the data
Stage 7: interpret the results
communicate via report

## Slide 6: Project management approach
scrum project management best for development project(complex solution and complex environment)
Best for delivering the solution as increments deliverable parts
Timeboxes are used to develop the solution incrementally
Aids in prioritising the scope of project in terms of Must have, should have, could have
The project methodology is best fit to deliver the project on the time.
Project backlog makes the things clear, understandable and easy.

## Slide 7: Project plan
Sprint 1(week 1&week 2)
Project agreement
Sprint 2(week 3 & week 4)
W3-project plan presentation
Sprint 3(week 5 & week 6)
W5-aquire the data and clean the data
W4-project proposal
W6-explore the data and methods
sprint 4( (week 7 & week 8)
W7- visualizing the dataset
W8-statistical prediction
Meeting with supervisor –once in a every week

## Slide 8: Contd…
Sprint 5(week 9&week 10)
  W9 register for project presentation and side by work on prediction modelling
  W10-break
Sprint 6(week 11 & week 12)
  W11-prediction and modelling of data
  W12-project presentation
Sprint 7(week 13 & week 14)
  Final submission(final report)
Meeting with supervisor –once in a every week

## Slide 9: Risks and mitigation steps:
Risk type | Risk description | Mitigation step
medium | Lack of availability of supervisor due to emergency condition or busy schedule | Set a schedule for weekly meeting. Direct communication over slack.
high | Solution does not meet requirements/unexpected solution | - Continuous incremental delivery of solutions and weekly feedback from supervisor
medium | Missing data points of interest or noisy data or error prone data | - Techniques like binning, normalizing, filling missing values etc.
low | Project does not meet deadlines | Follow project plan and keep few days in fortnight reserved for risk handling.

## Slide 10: refernceS:
BS ISO 21500:2012: Guidance on project management (2012). British Standards Institute
Schedlbauer, M. (2011, February 22). Requirements Prioritization Strategies. Retrieved from https https://www.projecttimes.com/articles/requirements-prioritization-strategies.html
V Dhar, Data Science and Prediction, Communications of the ACM, vol 56, No 12, December 2013.
C.-H. Kang, J.-R. Hwang, and K.-J. Li. Trajectory analysis for soccer players. In Data Mining Workshops, 2006. ICDM Workshops 2006. Sixth IEEE International Conference on, pages 377–381. IEEE, 2006.
Tobias Schreck, Member, IEEE, Daniel A. Keim, Member, IEEE, and Oliver Deussen. Feature-Driven Visual Analytics of Soccer Data.